## decision priority mat
Decision Priority Matrix
Department 1
Name | Owner | Impact | Effort Level | Urgency | Priority Outcome | Action | Timeline - Start | Timeline - End | Completion status
Monthly Presentation |  | High | Low | Medium | Quick Win / Do Now | Do now | 2022-04-06 | 2022-04-09 | Done
Code Debugging |  | Medium | High | High | Plan it / Do next | Do next | 2022-04-14 | 2022-04-22 | Done
[7 empty] | 2022-04-06 | 2022-04-22
Department 2
Name | Owner | Impact | Effort Level | Urgency | Priority Outcome | Action | Timeline - Start | Timeline - End | Completion status
3.2 Mobile Release |  | Low | High | Low | Time Sink / Deprioritize | Eliminate | 2022-04-05 | 2022-04-13 | Done
Design Testing |  | Low | High | Low | Time Sink / Deprioritize | Eliminate | 2022-04-14 | 2022-04-19 | Stuck
Project Analysis |  | High | Low | Medium | Quick Win / Do Now | Do now | 2022-04-13 | 2022-04-20 | Pending
UX Testing |  | Low | Low | Low | Filler task / Do when possible | Do next | 2022-04-21 | 2022-04-29 | Pending
[7 empty] | 2022-04-05 | 2022-04-29